## Projects
project_id | project_name | sector | district | asset_type | asset_ref | implementing_agency | project_status | start_date | planned_end_date | risk_rating | internal_risk_notes
prj-5001 | Highlands Bridge 79 | roads | highlands | water_point | asset-7087 | AgencyThree | cancelled | 2026-02-28 | 2027-12-05 | low | weather risk
prj-5002 | Riverbend School 23 | roads | riverbend | admin_building | asset-7829 | AgencyFour | delayed | 2024-01-13 | 2024-08-17 | low
prj-5003 | Central Borehole 11 | water | central | water_point | asset-7037 | AgencyThree | completed | 2025-05-06 | 2027-02-24 | low
prj-5004 | Riverbend Road 30 | schools | riverbend | school | sch-3005 | AgencyTwo | active | 2024-09-21 | 2025-09-28 | low | weather risk
prj-5005 | Riverbend Borehole 41 | roads | riverbend | road | asset-7238 | AgencyOne | active | 2024-02-09 | 2024-11-13 | medium | weather risk
prj-5006 | Central Borehole 31 | water | central | admin_building | asset-7265 | AgencyThree | completed | 2024-01-17 | 2025-04-12 | medium
prj-5007 | Riverbend Bridge 83 | roads | riverbend | road | asset-7523 | AgencyFour | planned | 2024-07-27 | 2025-09-23 | medium | weather risk
prj-5008 | North Clinic 38 | schools | north | school | sch-3021 | AgencyOne | active | 2025-01-03 | 2026-03-12 | high
prj-5009 | North Borehole 92 | roads | north | road | asset-7933 | AgencyThree | active | 2024-04-18 | 2026-04-01 | low
prj-5010 | Central Bridge 29 | clinics | central | facility | fac-4075 | AgencyFour | planned | 2026-01-13 | 2026-09-13 | low
prj-5011 | North School 25 | water | north | admin_building | asset-7817 | AgencyThree | planned | 2025-04-28 | 2027-01-15 | medium
prj-5012 | Central Office 53 | clinics | central | facility | fac-4047 | AgencyThree | active | 2024-11-18 | 2025-06-14 | medium | weather risk
prj-5013 | Riverbend Road 73 | roads | riverbend | road | asset-7936 | AgencyTwo | active | 2025-05-10 | 2027-04-19 | low | weather risk
prj-5014 | Central School 41 | clinics | central | facility | fac-4053 | AgencyOne | active | 2025-11-12 | 2026-07-01 | medium
prj-5015 | Central Bridge 22 | roads | central | road | asset-7589 | AgencyOne | active | 2026-03-02 | 2026-12-19 | high | weather risk
prj-5016 | Highlands Bridge 89 | water | highlands | admin_building | asset-7952 | AgencyTwo | active | 2024-04-13 | 2024-11-18 | high | weather risk
prj-5017 | North Office 38 | clinics | north | facility | fac-4068 | AgencyOne | completed | 2025-03-08 | 2026-06-03 | low | site access pending
prj-5018 | Highlands Clinic 53 | roads | highlands | water_point | asset-7605 | AgencyFour | active | 2024-04-20 | 2024-09-03 | low
prj-5019 | Central Road 1 | schools | central | school | sch-3049 | AgencyThree | active | 2024-05-17 | 2025-02-18 | medium
prj-5020 | Central Road 39 | water | central | water_point | asset-7449 | AgencyFour | active | 2026-01-09 | 2027-12-02 | low
prj-5021 | Riverbend Road 19 | roads | riverbend | admin_building | asset-7593 | AgencyOne | active | 2025-03-12 | 2026-03-29 | low
prj-5022 | Riverbend Bridge 45 | schools | riverbend | school | sch-3047 | AgencyThree | active | 2025-06-15 | 2026-06-24 | medium
prj-5023 | Central Borehole 97 | roads | central | water_point | asset-7449 | AgencyOne | active | 2024-06-22 | 2025-07-12 | high
prj-5024 | Riverbend Borehole 6 | clinics | riverbend | facility | fac-4019 | AgencyTwo | planned | 2025-07-19 | 2027-03-21 | medium
prj-5025 | Highlands Clinic 38 | roads | highlands | road | asset-7378 | AgencyOne | active | 2025-08-07 | 2027-01-15 | medium | site access pending
prj-5026 | Coast School 94 | schools | coast | school | sch-3008 | AgencyOne | active | 2025-03-18 | 2026-11-03 | low | site access pending
prj-5027 | Highlands Clinic 81 | clinics | highlands | facility | fac-4029 | AgencyOne | delayed | 2024-11-30 | 2025-08-07 | medium
prj-5028 | Central Office 81 | schools | central | school | sch-3060 | AgencyOne | planned | 2024-04-12 | 2025-12-26 | low
prj-5029 | Riverbend Office 64 | roads | riverbend | road | asset-7689 | AgencyThree | active | 2025-04-26 | 2025-12-27 | medium | site access pending
prj-5030 | Riverbend Clinic 72 | roads | riverbend | road | asset-7973 | AgencyTwo | active | 2026-01-10 | 2026-11-15 | low
prj-5031 | North Clinic 68 | schools | north | school | sch-3045 | AgencyTwo | active | 2025-01-24 | 2026-12-12 | low
prj-5032 | Highlands Borehole 46 | schools | highlands | school | sch-3057 | AgencyFour | active | 2025-05-11 | 2026-12-23 | medium | weather risk
prj-5033 | North Road 60 | roads | north | water_point | asset-7429 | AgencyThree | completed | 2024-11-29 | 2025-11-07 | medium
prj-5034 | Central Bridge 38 | water | central | water_point | asset-7721 | AgencyThree | active | 2025-05-10 | 2026-12-21 | medium | site access pending
prj-5035 | Coast Clinic 57 | water | coast | water_point | asset-7062 | AgencyFour | active | 2024-11-26 | 2025-11-18 | medium | weather risk
prj-5036 | Coast Road 74 | roads | coast | water_point | asset-7497 | AgencyTwo | delayed | 2024-12-13 | 2025-04-28 | low | weather risk
prj-5037 | Highlands Office 3 | water | highlands | road | asset-7970 | AgencyFour | completed | 2025-09-17 | 2026-11-18 | low
prj-5038 | Riverbend Borehole 26 | roads | riverbend | water_point | asset-7785 | AgencyTwo | delayed | 2024-03-05 | 2024-07-23 | medium
prj-5039 | Central Clinic 28 | schools | central | school | sch-3046 | AgencyTwo | active | 2026-03-31 | 2026-12-11 | high
prj-5040 | North Bridge 21 | clinics | north | facility | fac-4003 | AgencyThree | delayed | 2025-06-23 | 2026-01-03 | medium | weather risk
prj-5041 | Central Office 52 | roads | central | admin_building | asset-7253 | AgencyTwo | planned | 2026-02-06 | 2026-09-10 | medium | weather risk
prj-5042 | Highlands Bridge 2 | schools | highlands | school | sch-3056 | AgencyTwo | planned | 2024-03-16 | 2025-11-12 | medium | weather risk
prj-5043 | Riverbend School 36 | roads | riverbend | water_point | asset-7198 | AgencyFour | delayed | 2024-11-15 | 2026-01-10 | medium
prj-5044 | Central Borehole 36 | roads | central | admin_building | asset-7590 | AgencyFour | active | 2024-10-25 | 2026-04-07 | low | weather risk
prj-5045 | Riverbend Clinic 29 | roads | riverbend | admin_building | asset-7250 | AgencyOne | active | 2025-05-23 | 2026-09-28 | high
prj-5046 | Central Bridge 72 | roads | central | water_point | asset-7488 | AgencyTwo | active | 2025-10-20 | 2026-12-02 | low
prj-5047 | Coast Bridge 99 | roads | coast | admin_building | asset-7255 | AgencyFour | planned | 2025-02-16 | 2026-09-13 | medium | site access pending
prj-5048 | Central School 89 | roads | central | water_point | asset-7854 | AgencyTwo | active | 2024-11-25 | 2026-09-24 | medium
prj-5049 | Highlands Borehole 72 | schools | highlands | school | sch-3035 | AgencyOne | active | 2025-10-29 | 2026-09-25 | low | weather risk
prj-5050 | Central Road 26 | clinics | central | facility | fac-4010 | AgencyFour | active | 2026-02-14 | 2026-05-28 | low
prj-5051 | North Clinic 2 | schools | north | school | sch-3057 | AgencyThree | active | 2024-06-23 | 2026-03-12 | medium | weather risk
prj-5052 | South Borehole 84 | roads | south | admin_building | asset-7944 | AgencyTwo | completed | 2024-10-04 | 2026-06-21 | low
prj-5053 | Riverbend Clinic 60 | roads | riverbend | road | asset-7822 | AgencyTwo | active | 2026-01-01 | 2027-04-16 | medium
prj-5054 | Coast Road 20 | clinics | coast | facility | fac-4018 | AgencyFour | active | 2026-01-02 | 2027-07-31 | low | weather risk
prj-5055 | Coast Bridge 8 | roads | coast | water_point | asset-7718 | AgencyFour | active | 2025-12-11 | 2026-06-15 | medium
prj-5056 | North School 55 | water | north | admin_building | asset-7572 | AgencyThree | completed | 2024-12-19 | 2025-04-02 | high
prj-5057 | Highlands Bridge 94 | roads | highlands | water_point | asset-7574 | AgencyTwo | active | 2025-11-06 | 2026-08-30 | low | site access pending
prj-5058 | Central Office 79 | roads | central | road | asset-7129 | AgencyFour | delayed | 2025-08-24 | 2026-12-19 | low
prj-5059 | North Bridge 42 | roads | north | road | asset-7221 | AgencyOne | planned | 2025-09-21 | 2026-05-19 | low | weather risk
prj-5060 | North Road 72 | schools | north | school | sch-3033 | AgencyFour | delayed | 2025-03-11 | 2026-10-05 | low
prj-5061 | Central Road 82 | roads | central | water_point | asset-7363 | AgencyThree | active | 2025-06-18 | 2026-08-06 | medium | site access pending
prj-5062 | Highlands Office 45 | schools | highlands | school | sch-3036 | AgencyTwo | active | 2025-12-12 | 2026-11-23 | medium | weather risk
prj-5063 | Central Clinic 48 | roads | central | water_point | asset-7789 | AgencyTwo | active | 2026-01-15 | 2027-06-23 | low | site access pending
prj-5064 | South School 13 | clinics | south | facility | fac-4026 | AgencyThree | active | 2025-06-22 | 2026-04-07 | low
prj-5065 | Riverbend Bridge 90 | clinics | riverbend | facility | fac-4002 | AgencyThree | active | 2024-02-04 | 2025-02-09 | medium | weather risk
prj-5066 | North Clinic 23 | roads | north | admin_building | asset-7843 | AgencyFour | planned | 2026-01-05 | 2027-07-31 | high | weather risk
prj-5067 | Riverbend Office 95 | schools | riverbend | school | sch-3035 | AgencyTwo | delayed | 2024-02-09 | 2025-05-22 | low | site access pending
prj-5068 | North School 13 | schools | north | school | sch-3027 | AgencyThree | delayed | 2024-05-02 | 2024-09-26 | medium
prj-5069 | North Borehole 93 | clinics | north | facility | fac-4079 | AgencyThree | delayed | 2024-12-06 | 2026-01-24 | high | site access pending
prj-5070 | Coast Office 35 | water | coast | water_point | asset-7426 | AgencyOne | delayed | 2025-11-16 | 2026-04-17 | low | site access pending
prj-5071 | North School 36 | roads | north | admin_building | asset-7203 | AgencyThree | active | 2025-02-23 | 2025-11-17 | medium
prj-5072 | Central Road 94 | roads | central | admin_building | asset-7088 | AgencyOne | active | 2025-04-19 | 2025-10-16 | low
prj-5073 | Riverbend Bridge 93 | roads | riverbend | road | asset-7785 | AgencyTwo | active | 2024-01-11 | 2024-11-18 | medium | weather risk
prj-5074 | Riverbend Road 36 | roads | riverbend | road | asset-7765 | AgencyTwo | delayed | 2024-05-15 | 2025-06-26 | low
prj-5075 | Central School 12 | water | central | road | asset-7279 | AgencyFour | completed | 2024-06-30 | 2025-07-27 | low | weather risk
prj-5076 | Central Road 69 | roads | central | admin_building | asset-7535 | AgencyTwo | active | 2025-10-08 | 2026-06-29 | low | weather risk
prj-5077 | Central Bridge 66 | clinics | central | facility | fac-4083 | AgencyTwo | delayed | 2026-03-26 | 2027-04-15 | low
prj-5078 | Central Borehole 42 | roads | central | road | asset-7944 | AgencyThree | active | 2025-11-05 | 2026-08-12 | medium | weather risk
prj-5079 | Riverbend Road 54 | water | riverbend | road | asset-7330 | AgencyFour | delayed | 2025-10-06 | 2027-01-06 | high
prj-5080 | Riverbend Bridge 57 | roads | riverbend | road | asset-7191 | AgencyFour | completed | 2024-11-09 | 2025-07-23 | medium | site access pending
prj-5081 | Riverbend Clinic 87 | water | riverbend | admin_building | asset-7408 | AgencyFour | active | 2024-09-06 | 2025-08-20 | medium
prj-5082 | Coast Borehole 52 | roads | coast | road | asset-7781 | AgencyOne | completed | 2025-06-03 | 2025-12-20 | medium
prj-5083 | North Road 85 | roads | north | water_point | asset-7907 | AgencyThree | active | 2025-12-15 | 2027-09-02 | low | site access pending
prj-5084 | North Clinic 22 | schools | north | school | sch-3006 | AgencyFour | active | 2026-02-23 | 2026-10-15 | medium | weather risk
prj-5085 | North Bridge 93 | roads | north | road | asset-7308 | AgencyTwo | active | 2024-07-08 | 2025-06-04 | high | weather risk
prj-5086 | Riverbend Office 28 | roads | riverbend | water_point | asset-7005 | AgencyFour | active | 2024-12-18 | 2025-06-28 | medium | weather risk
prj-5087 | Highlands Clinic 99 | water | highlands | admin_building | asset-7248 | AgencyThree | delayed | 2024-04-08 | 2025-08-07 | low | site access pending
prj-5088 | Highlands Clinic 86 | schools | highlands | school | sch-3047 | AgencyOne | completed | 2025-09-03 | 2027-01-09 | medium
prj-5089 | Riverbend Bridge 83 | roads | riverbend | road | asset-7377 | AgencyTwo | active | 2025-05-28 | 2025-08-27 | medium | weather risk
prj-5090 | North Road 37 | roads | north | road | asset-7309 | AgencyThree | active | 2024-12-13 | 2026-04-10 | medium | weather risk
prj-5091 | Highlands Clinic 11 | roads | highlands | road | asset-7267 | AgencyThree | completed | 2025-03-07 | 2025-12-05 | low
prj-5092 | North Office 59 | water | north | water_point | asset-7822 | AgencyOne | delayed | 2024-06-13 | 2025-08-03 | low | weather risk
prj-5093 | Coast Borehole 58 | water | coast | water_point | asset-7432 | AgencyThree | delayed | 2024-11-06 | 2026-04-15 | low
prj-5094 | Riverbend Borehole 98 | schools | riverbend | school | sch-3055 | AgencyFour | active | 2025-01-08 | 2025-07-31 | medium | weather risk
prj-5095 | North Clinic 7 | schools | north | school | sch-3001 | AgencyFour | active | 2025-12-25 | 2027-11-19 | low | weather risk
prj-5096 | North Office 38 | roads | north | water_point | asset-7471 | AgencyOne | active | 2025-09-05 | 2026-12-17 | low
prj-5097 | North School 94 | water | north | water_point | asset-7427 | AgencyOne | planned | 2024-11-28 | 2025-12-27 | medium
prj-5098 | Central School 45 | water | central | road | asset-7086 | AgencyFour | active | 2024-05-09 | 2025-01-02 | medium | weather risk
prj-5099 | Central Bridge 19 | water | central | admin_building | asset-7840 | AgencyOne | active | 2025-04-14 | 2025-08-23 | low
prj-5100 | South Road 96 | roads | south | road | asset-7345 | AgencyThree | completed | 2026-02-06 | 2027-03-12 | medium
prj-5101 | Highlands School 79 | schools | highlands | school | sch-3006 | AgencyTwo | delayed | 2025-03-19 | 2025-10-14 | medium
prj-5102 | North School 65 | water | north | admin_building | asset-7484 | AgencyOne | active | 2025-03-23 | 2026-03-29 | medium | site access pending
prj-5103 | Coast Office 17 | water | coast | admin_building | asset-7291 | AgencyThree | active | 2025-02-20 | 2025-12-19 | low | weather risk
prj-5104 | Riverbend Bridge 79 | roads | riverbend | admin_building | asset-7325 | AgencyThree | planned | 2024-08-18 | 2024-12-04 | medium | site access pending
prj-5105 | Riverbend Clinic 72 | schools | riverbend | school | sch-3030 | AgencyOne | active | 2025-10-12 | 2027-09-11 | low | weather risk
prj-5106 | Central Office 50 | roads | central | water_point | asset-7155 | AgencyThree | active | 2026-01-30 | 2027-09-22 | low | site access pending
prj-5107 | Riverbend Road 96 | water | riverbend | admin_building | asset-7990 | AgencyThree | planned | 2025-05-13 | 2027-03-08 | high
prj-5108 | Highlands Borehole 56 | roads | highlands | water_point | asset-7690 | AgencyFour | active | 2024-06-08 | 2026-04-27 | low
prj-5109 | North Clinic 78 | clinics | north | facility | fac-4037 | AgencyOne | active | 2025-05-17 | 2026-04-12 | low | site access pending
prj-5110 | North Road 54 | roads | north | road | asset-7584 | AgencyThree | active | 2024-06-11 | 2025-10-24 | medium

## Contracts
contract_id | project_id | contractor_ref | procurement_method | contract_status | contract_value | signed_on | contractor_bank_ref
ctr-9001 | prj-5001 | vendor-614 | open_tender | signed | 664144.61 | 2025-10-10 | ****-6206
ctr-9002 | prj-5002 | vendor-945 | open_tender | closed | 373650.74 | 2025-04-20 | ****-5690
ctr-9003 | prj-5003 | vendor-949 | open_tender | closed | 303040.5 | 2024-01-04 | ****-9727
ctr-9004 | prj-5003 | vendor-694 | open_tender | active | 133341.65 | 2024-04-10 | ****-7280
ctr-9005 | prj-5003 | vendor-733 | restricted_tender | terminated | 310668.88 | 2025-10-13 | ****-1475
ctr-9006 | prj-5004 | vendor-123 | restricted_tender | active | 64976.83 | 2025-08-07 | ****-7697
ctr-9007 | prj-5005 | vendor-123 | open_tender | active | 356575.59 | 2024-04-03 | ****-7066
ctr-9008 | prj-5006 | vendor-568 | direct_award | active | 416282.73 | 2024-07-16 | ****-3644
ctr-9009 | prj-5006 | vendor-430 | open_tender | closed | 135532.19 | 2025-12-30 | ****-4273
ctr-9010 | prj-5007 | vendor-800 | open_tender | draft | 435313.68 | 2025-04-15 | ****-5014
ctr-9011 | prj-5008 | vendor-922 | framework | closed | 729739.94 | 2025-05-27 | ****-2821
ctr-9012 | prj-5009 | vendor-107 | open_tender | closed | 123653.61 | 2025-04-18 | ****-2144
ctr-9013 | prj-5010 | vendor-172 | restricted_tender | active | 392226.8 | 2025-04-26 | ****-7313
ctr-9014 | prj-5010 | vendor-832 | restricted_tender | terminated | 663100.99 | 2025-07-04 | ****-2982
ctr-9015 | prj-5011 | vendor-399 | restricted_tender | active | 22671.49 | 2025-05-07 | ****-1979
ctr-9016 | prj-5011 | vendor-509 | restricted_tender | closed | 545237.15 | 2024-02-10 | ****-6953
ctr-9017 | prj-5012 | vendor-249 | open_tender | active | 324298.46 | 2024-05-07 | ****-2697
ctr-9018 | prj-5012 | vendor-839 | restricted_tender | closed | 436959.93 | 2026-03-21 | ****-2831
ctr-9019 | prj-5013 | vendor-315 | open_tender | active | 685166.07 | 2026-03-25 | ****-8906
ctr-9020 | prj-5014 | vendor-870 | open_tender | active | 346390.31 | 2025-12-27 | ****-9053
ctr-9021 | prj-5015 | vendor-816 | open_tender | signed | 336280.69 | 2026-03-17 | ****-8378
ctr-9022 | prj-5016 | vendor-126 | open_tender | draft | 109315.63 | 2025-06-18 | ****-5725
ctr-9023 | prj-5017 | vendor-681 | open_tender | active | 221957.63 | 2026-01-03 | ****-3593
ctr-9024 | prj-5018 | vendor-250 | open_tender | active | 224685.31 | 2026-01-31 | ****-3106
ctr-9025 | prj-5019 | vendor-251 | direct_award | signed | 174798.93 | 2024-08-04 | ****-5963
ctr-9026 | prj-5020 | vendor-588 | open_tender | closed | 560365.64 | 2025-06-13 | ****-7649
ctr-9027 | prj-5021 | vendor-635 | open_tender | active | 121128.26 | 2025-05-28 | ****-6149
ctr-9028 | prj-5022 | vendor-279 | direct_award | active | 130995.05 | 2025-06-21 | ****-8897
ctr-9029 | prj-5023 | vendor-311 | open_tender | active | 53240.68 | 2024-08-18 | ****-6067
ctr-9030 | prj-5024 | vendor-465 | open_tender | closed | 593009.31 | 2025-10-27 | ****-4226
ctr-9031 | prj-5025 | vendor-333 | restricted_tender | active | 14089.59 | 2026-02-03 | ****-9587
ctr-9032 | prj-5026 | vendor-168 | open_tender | draft | 471669.51 | 2024-12-03 | ****-9313
ctr-9033 | prj-5026 | vendor-917 | open_tender | terminated | 635721.19 | 2025-07-04 | ****-2301
ctr-9034 | prj-5028 | vendor-333 | open_tender | signed | 555879.65 | 2025-12-07 | ****-5015
ctr-9035 | prj-5029 | vendor-193 | open_tender | draft | 458807.59 | 2025-07-19 | ****-5546
ctr-9036 | prj-5029 | vendor-410 | restricted_tender | closed | 688512.79 | 2024-05-15 | ****-9561
ctr-9037 | prj-5031 | vendor-426 | restricted_tender | active | 350882.11 | 2025-07-03 | ****-1836
ctr-9038 | prj-5032 | vendor-202 | open_tender | active | 334214.06 | 2025-05-02 | ****-4234
ctr-9039 | prj-5032 | vendor-695 | open_tender | signed | 367986.85 | 2025-08-05 | ****-1157
ctr-9040 | prj-5033 | vendor-703 | direct_award | closed | 334768.15 | 2025-10-20 | ****-4191
ctr-9041 | prj-5034 | vendor-715 | restricted_tender | active | 5368.87 | 2026-02-11 | ****-7671
ctr-9042 | prj-5034 | vendor-390 | open_tender | active | 249836.35 | 2025-05-09 | ****-9424
ctr-9043 | prj-5035 | vendor-416 | open_tender | closed | 190521.39 | 2024-10-08 | ****-9242
ctr-9044 | prj-5035 | vendor-106 | restricted_tender | signed | 568676.11 | 2024-07-05 | ****-8988
ctr-9045 | prj-5035 | vendor-167 | open_tender | terminated | 355527.22 | 2024-06-16 | ****-3929
ctr-9046 | prj-5036 | vendor-942 | restricted_tender | signed | 647212.27 | 2024-12-16 | ****-9824
ctr-9047 | prj-5036 | vendor-613 | open_tender | closed | 573325.22 | 2024-08-06 | ****-6033
ctr-9048 | prj-5037 | vendor-684 | restricted_tender | active | 515136.01 | 2025-09-16 | ****-4445
ctr-9049 | prj-5038 | vendor-724 | open_tender | signed | 300198.79 | 2024-06-24 | ****-3587
ctr-9050 | prj-5038 | vendor-898 | restricted_tender | active | 389767.39 | 2025-04-30 | ****-7830
ctr-9051 | prj-5039 | vendor-248 | open_tender | signed | 701075.83 | 2024-11-06 | ****-7075
ctr-9052 | prj-5039 | vendor-415 | open_tender | closed | 622777.31 | 2024-11-18 | ****-8368
ctr-9053 | prj-5040 | vendor-518 | open_tender | active | 572855.94 | 2025-02-17 | ****-1906
ctr-9054 | prj-5041 | vendor-313 | restricted_tender | terminated | 576451.21 | 2024-01-20 | ****-4313
ctr-9055 | prj-5042 | vendor-433 | open_tender | closed | 22640.85 | 2025-03-13 | ****-7265
ctr-9056 | prj-5042 | vendor-550 | restricted_tender | closed | 599118.59 | 2025-09-24 | ****-9240
ctr-9057 | prj-5043 | vendor-147 | open_tender | signed | 247484.86 | 2025-05-06 | ****-8698
ctr-9058 | prj-5043 | vendor-355 | restricted_tender | active | 720000.12 | 2025-12-24 | ****-8979
ctr-9059 | prj-5044 | vendor-382 | restricted_tender | active | 80572.74 | 2025-10-16 | ****-6614
ctr-9060 | prj-5045 | vendor-432 | open_tender | signed | 356521.45 | 2026-02-06 | ****-2212
ctr-9061 | prj-5046 | vendor-687 | restricted_tender | closed | 656093.21 | 2025-08-26 | ****-5896
ctr-9062 | prj-5046 | vendor-881 | open_tender | signed | 187693.87 | 2025-08-09 | ****-9955
ctr-9063 | prj-5046 | vendor-243 | restricted_tender | active | 613895.94 | 2025-12-07 | ****-1358
ctr-9064 | prj-5047 | vendor-891 | open_tender | closed | 534995 | 2024-11-17 | ****-6918
ctr-9065 | prj-5047 | vendor-571 | open_tender | closed | 142184.32 | 2025-04-24 | ****-4730
ctr-9066 | prj-5048 | vendor-243 | open_tender | terminated | 197974.24 | 2025-09-10 | ****-1379
ctr-9067 | prj-5049 | vendor-161 | open_tender | active | 367336.36 | 2024-02-19 | ****-9657
ctr-9068 | prj-5050 | vendor-994 | open_tender | draft | 330719.15 | 2024-02-02 | ****-9261
ctr-9069 | prj-5050 | vendor-749 | restricted_tender | closed | 371547.06 | 2025-08-11 | ****-6468
ctr-9070 | prj-5050 | vendor-644 | open_tender | draft | 73646.92 | 2025-07-25 | ****-2840
ctr-9071 | prj-5051 | vendor-869 | open_tender | closed | 432574.3 | 2025-04-24 | ****-4127
ctr-9072 | prj-5053 | vendor-766 | restricted_tender | active | 667570.06 | 2026-01-26 | ****-3493
ctr-9073 | prj-5053 | vendor-899 | open_tender | signed | 433541.71 | 2025-04-09 | ****-9646
ctr-9074 | prj-5054 | vendor-106 | restricted_tender | active | 21005.23 | 2025-08-11 | ****-5813
ctr-9075 | prj-5054 | vendor-254 | restricted_tender | active | 11360.74 | 2024-11-26 | ****-7998
ctr-9076 | prj-5055 | vendor-888 | open_tender | active | 248331.36 | 2025-04-13 | ****-4282
ctr-9077 | prj-5056 | vendor-293 | direct_award | closed | 537603.83 | 2025-08-13 | ****-3500
ctr-9078 | prj-5056 | vendor-716 | restricted_tender | signed | 140282.11 | 2024-01-27 | ****-9739
ctr-9079 | prj-5057 | vendor-991 | open_tender | signed | 264647.1 | 2024-03-11 | ****-6365
ctr-9080 | prj-5057 | vendor-534 | open_tender | signed | 160561.4 | 2024-11-06 | ****-3675
ctr-9081 | prj-5057 | vendor-127 | framework | signed | 690309.3 | 2026-03-01 | ****-6821
ctr-9082 | prj-5058 | vendor-554 | direct_award | active | 626447.15 | 2025-01-19 | ****-1416
ctr-9083 | prj-5059 | vendor-303 | direct_award | signed | 41664.65 | 2025-03-25 | ****-7540
ctr-9084 | prj-5059 | vendor-618 | open_tender | active | 611802.07 | 2024-04-05 | ****-3868
ctr-9085 | prj-5060 | vendor-858 | restricted_tender | signed | 568671.74 | 2024-05-03 | ****-9013
ctr-9086 | prj-5060 | vendor-192 | restricted_tender | closed | 241075.29 | 2024-07-14 | ****-4446
ctr-9087 | prj-5060 | vendor-116 | restricted_tender | active | 195186.98 | 2024-04-24 | ****-8486
ctr-9088 | prj-5062 | vendor-544 | open_tender | closed | 269237.42 | 2024-11-13 | ****-2069
ctr-9089 | prj-5062 | vendor-766 | direct_award | active | 175872.33 | 2025-12-19 | ****-2383
ctr-9090 | prj-5063 | vendor-146 | open_tender | active | 713725.31 | 2024-10-08 | ****-6296
ctr-9091 | prj-5064 | vendor-811 | open_tender | active | 100321.49 | 2024-06-08 | ****-3297
ctr-9092 | prj-5065 | vendor-480 | open_tender | active | 161320.07 | 2026-01-27 | ****-5801
ctr-9093 | prj-5066 | vendor-859 | restricted_tender | active | 135104.92 | 2025-06-15 | ****-3480
ctr-9094 | prj-5067 | vendor-130 | restricted_tender | active | 694091.09 | 2026-03-16 | ****-3660
ctr-9095 | prj-5067 | vendor-129 | open_tender | active | 470857.8 | 2024-09-28 | ****-6260
ctr-9096 | prj-5068 | vendor-147 | open_tender | closed | 30495.97 | 2024-05-27 | ****-7679
ctr-9097 | prj-5068 | vendor-202 | open_tender | closed | 543279.42 | 2024-06-22 | ****-3591
ctr-9098 | prj-5070 | vendor-525 | open_tender | terminated | 88745.89 | 2025-05-02 | ****-8609
ctr-9099 | prj-5070 | vendor-418 | direct_award | active | 105132.02 | 2025-09-09 | ****-1011
ctr-9100 | prj-5071 | vendor-728 | direct_award | signed | 245542.96 | 2025-07-06 | ****-6989
ctr-9101 | prj-5072 | vendor-228 | open_tender | active | 624161.57 | 2025-08-07 | ****-4215
ctr-9102 | prj-5072 | vendor-861 | open_tender | signed | 707005.4 | 2024-08-18 | ****-2346
ctr-9103 | prj-5074 | vendor-436 | direct_award | signed | 173536.44 | 2024-07-08 | ****-5933
ctr-9104 | prj-5075 | vendor-435 | open_tender | active | 390093.75 | 2024-09-30 | ****-3157
ctr-9105 | prj-5075 | vendor-747 | open_tender | active | 436629.58 | 2024-02-05 | ****-7308
ctr-9106 | prj-5077 | vendor-265 | open_tender | signed | 30414.96 | 2026-03-24 | ****-4896
ctr-9107 | prj-5078 | vendor-562 | open_tender | active | 643971.94 | 2024-07-11 | ****-7646
ctr-9108 | prj-5079 | vendor-771 | open_tender | signed | 332697.93 | 2026-02-01 | ****-5576
ctr-9109 | prj-5079 | vendor-449 | restricted_tender | closed | 256254.67 | 2024-07-09 | ****-5182
ctr-9110 | prj-5079 | vendor-784 | restricted_tender | active | 413931.09 | 2025-11-10 | ****-2581
ctr-9111 | prj-5080 | vendor-656 | restricted_tender | signed | 587555.93 | 2025-03-12 | ****-1416
ctr-9112 | prj-5080 | vendor-663 | open_tender | signed | 345787.91 | 2024-04-23 | ****-2970
ctr-9113 | prj-5081 | vendor-987 | open_tender | active | 342160.79 | 2025-07-20 | ****-2359
ctr-9114 | prj-5081 | vendor-245 | framework | signed | 615919.83 | 2025-06-07 | ****-4192
ctr-9115 | prj-5082 | vendor-715 | open_tender | draft | 551392.18 | 2024-12-28 | ****-9611
ctr-9116 | prj-5082 | vendor-471 | restricted_tender | active | 400268.35 | 2024-02-18 | ****-9735
ctr-9117 | prj-5083 | vendor-796 | restricted_tender | terminated | 129231.33 | 2024-06-11 | ****-2640
ctr-9118 | prj-5084 | vendor-653 | restricted_tender | active | 633212.9 | 2026-02-08 | ****-3491
ctr-9119 | prj-5085 | vendor-499 | restricted_tender | closed | 212423.93 | 2025-02-14 | ****-5857
ctr-9120 | prj-5085 | vendor-239 | direct_award | terminated | 670839.65 | 2025-04-24 | ****-6274
ctr-9121 | prj-5085 | vendor-313 | restricted_tender | signed | 60778.51 | 2025-12-26 | ****-6105
ctr-9122 | prj-5086 | vendor-247 | restricted_tender | terminated | 49120.56 | 2025-02-24 | ****-3298
ctr-9123 | prj-5086 | vendor-905 | open_tender | signed | 729210.78 | 2024-09-05 | ****-7410
ctr-9124 | prj-5086 | vendor-172 | open_tender | active | 445605.22 | 2024-09-11 | ****-6741
ctr-9125 | prj-5087 | vendor-310 | direct_award | signed | 304073.2 | 2026-01-13 | ****-3487
ctr-9126 | prj-5088 | vendor-418 | restricted_tender | closed | 13022.93 | 2024-04-30 | ****-9529
ctr-9127 | prj-5089 | vendor-941 | restricted_tender | active | 177974.97 | 2025-03-24 | ****-5895
ctr-9128 | prj-5090 | vendor-996 | restricted_tender | active | 57450.04 | 2026-02-11 | ****-6593
ctr-9129 | prj-5091 | vendor-536 | framework | active | 668881.98 | 2024-04-25 | ****-8643
ctr-9130 | prj-5092 | vendor-330 | direct_award | active | 596869.43 | 2026-02-15 | ****-5769
ctr-9131 | prj-5093 | vendor-990 | open_tender | closed | 720002.16 | 2025-01-06 | ****-4953
ctr-9132 | prj-5094 | vendor-985 | open_tender | closed | 327195.6 | 2024-02-28 | ****-2723
ctr-9133 | prj-5094 | vendor-436 | restricted_tender | closed | 550669.76 | 2024-09-14 | ****-9320
ctr-9134 | prj-5095 | vendor-348 | restricted_tender | terminated | 66904.55 | 2024-04-13 | ****-8955
ctr-9135 | prj-5096 | vendor-674 | open_tender | active | 202986.85 | 2026-03-10 | ****-8993
ctr-9136 | prj-5097 | vendor-143 | restricted_tender | active | 653443.13 | 2025-11-14 | ****-7268
ctr-9137 | prj-5098 | vendor-220 | restricted_tender | closed | 715783.25 | 2025-08-12 | ****-2555
ctr-9138 | prj-5099 | vendor-934 | open_tender | active | 533432.44 | 2025-09-10 | ****-7911
ctr-9139 | prj-5099 | vendor-972 | open_tender | closed | 263741.82 | 2026-03-18 | ****-8212
ctr-9140 | prj-5099 | vendor-785 | open_tender | closed | 32770.8 | 2025-02-12 | ****-8074
ctr-9141 | prj-5100 | vendor-399 | open_tender | signed | 474738.35 | 2024-12-02 | ****-2618
ctr-9142 | prj-5100 | vendor-938 | direct_award | closed | 548147.74 | 2024-09-16 | ****-6875
ctr-9143 | prj-5100 | vendor-902 | restricted_tender | active | 724363.5 | 2024-10-10 | ****-8307
ctr-9144 | prj-5102 | vendor-763 | framework | signed | 596262.56 | 2024-08-02 | ****-9966
ctr-9145 | prj-5103 | vendor-441 | open_tender | active | 612524.74 | 2025-05-26 | ****-2456
ctr-9146 | prj-5104 | vendor-203 | open_tender | closed | 724598.2 | 2024-11-20 | ****-6010
ctr-9147 | prj-5105 | vendor-874 | open_tender | active | 468240.8 | 2025-10-16 | ****-4050
ctr-9148 | prj-5105 | vendor-925 | open_tender | signed | 532010.08 | 2024-12-25 | ****-6521
ctr-9149 | prj-5105 | vendor-116 | open_tender | active | 123616.94 | 2024-06-21 | ****-6288
ctr-9150 | prj-5106 | vendor-874 | restricted_tender | closed | 526670.08 | 2025-07-27 | ****-5853
ctr-9151 | prj-5107 | vendor-828 | open_tender | active | 61571.84 | 2024-04-05 | ****-2483
ctr-9152 | prj-5108 | vendor-645 | direct_award | active | 201210.68 | 2026-01-03 | ****-6573
ctr-9153 | prj-5109 | vendor-728 | open_tender | active | 634532.07 | 2026-01-23 | ****-5815
ctr-9154 | prj-5110 | vendor-661 | open_tender | terminated | 334689.36 | 2024-02-11 | ****-5028

## Milestones
milestone_id | project_id | milestone_name | milestone_status | due_date | completed_on | delay_reason | site_observation_notes
mil-10001 | prj-5001 | Foundation | blocked | 2024-06-27 |  | supply_chain | inspector visit done
mil-10002 | prj-5001 | Foundation | completed | 2026-09-10 | 2025-01-08 | none
mil-10003 | prj-5002 | Roofing | delayed | 2025-10-08 |  | funding_gap | inspector visit done
mil-10004 | prj-5002 | Handover | in_progress | 2025-11-14 |  | none | observation pending
mil-10005 | prj-5002 | Walls | in_progress | 2026-08-25 |  | none
mil-10006 | prj-5002 | Handover | blocked | 2025-01-27 |  | supply_chain
mil-10007 | prj-5002 | Finishing | in_progress | 2025-12-04 |  | none | observation pending
mil-10008 | prj-5003 | Roofing | delayed | 2026-02-09 |  | funding_gap | inspector visit done
mil-10009 | prj-5003 | Site preparation | in_progress | 2026-10-05 |  | none | observation pending
mil-10010 | prj-5003 | Roofing | blocked | 2024-11-23 |  | weather
mil-10011 | prj-5004 | Handover | pending | 2026-04-30 |  | none
mil-10012 | prj-5004 | Roofing | pending | 2026-02-03 |  | none | inspector visit done
mil-10013 | prj-5004 | Foundation | in_progress | 2025-09-06 |  | none
mil-10014 | prj-5004 | Finishing | completed | 2026-11-14 | 2025-11-03 | none | inspector visit done
mil-10015 | prj-5004 | Finishing | blocked | 2026-01-22 |  | weather
mil-10016 | prj-5005 | Finishing | blocked | 2026-02-19 |  | supply_chain | inspector visit done
mil-10017 | prj-5005 | Site preparation | delayed | 2024-12-01 | 2024-07-17 | weather
mil-10018 | prj-5006 | Roofing | completed | 2026-05-19 | 2026-05-03 | none | observation pending
mil-10019 | prj-5007 | Walls | pending | 2025-05-18 |  | none | observation pending
mil-10020 | prj-5007 | Walls | completed | 2024-12-06 | 2024-08-06 | none | inspector visit done
mil-10021 | prj-5007 | Site preparation | blocked | 2026-03-11 |  | funding_gap
mil-10022 | prj-5007 | Site preparation | delayed | 2024-08-02 |  | weather | inspector visit done
mil-10023 | prj-5008 | Finishing | completed | 2024-06-05 | 2024-06-21 | none
mil-10024 | prj-5008 | Handover | completed | 2026-10-28 | 2024-08-11 | none | inspector visit done
mil-10025 | prj-5008 | Site preparation | completed | 2024-12-04 | 2024-10-16 | none
mil-10026 | prj-5008 | Finishing | delayed | 2026-12-22 |  | community_consultation | inspector visit done
mil-10027 | prj-5008 | Walls | pending | 2026-09-17 | 2025-08-30 | none
mil-10028 | prj-5009 | Roofing | pending | 2026-05-01 |  | none
mil-10029 | prj-5009 | Roofing | in_progress | 2024-11-06 |  | none | observation pending
mil-10030 | prj-5009 | Roofing | blocked | 2026-04-16 |  | supply_chain | inspector visit done
mil-10031 | prj-5009 | Handover | in_progress | 2025-07-19 |  | none | observation pending
mil-10032 | prj-5009 | Finishing | delayed | 2026-10-08 |  | permits | observation pending
mil-10033 | prj-5010 | Roofing | in_progress | 2024-10-17 |  | none | observation pending
mil-10034 | prj-5010 | Finishing | completed | 2024-08-24 | 2024-08-02 | weather
mil-10035 | prj-5010 | Handover | completed | 2025-07-04 | 2024-11-04 | none
mil-10036 | prj-5010 | Walls | completed | 2025-11-23 | 2024-07-13 | none
mil-10037 | prj-5011 | Site preparation | delayed | 2026-01-06 |  | weather
mil-10038 | prj-5011 | Finishing | blocked | 2025-06-30 |  | community_consultation | inspector visit done
mil-10039 | prj-5011 | Foundation | in_progress | 2026-05-17 |  | none | inspector visit done
mil-10040 | prj-5011 | Site preparation | delayed | 2024-08-14 |  | funding_gap
mil-10041 | prj-5011 | Foundation | blocked | 2024-12-28 |  | supply_chain
mil-10042 | prj-5012 | Roofing | delayed | 2025-06-16 | 2024-12-23 | supply_chain
mil-10043 | prj-5012 | Roofing | completed | 2026-05-29 | 2026-03-04 | none
mil-10044 | prj-5012 | Foundation | completed | 2025-07-31 | 2025-07-27 | none
mil-10045 | prj-5012 | Handover | delayed | 2025-10-13 |  | community_consultation
mil-10046 | prj-5012 | Site preparation | delayed | 2024-10-10 |  | supply_chain | observation pending
mil-10047 | prj-5013 | Walls | in_progress | 2026-06-28 |  | none | observation pending
mil-10048 | prj-5013 | Roofing | completed | 2025-03-19 | 2025-03-19 | none
mil-10049 | prj-5014 | Roofing | delayed | 2024-08-28 |  | funding_gap
mil-10050 | prj-5014 | Foundation | completed | 2024-09-23 | 2024-07-29 | none | observation pending
mil-10051 | prj-5014 | Handover | pending | 2026-05-12 |  | none | observation pending
mil-10052 | prj-5014 | Foundation | pending | 2026-02-02 |  | none | inspector visit done
mil-10053 | prj-5015 | Walls | pending | 2024-06-15 |  | none | inspector visit done
mil-10054 | prj-5015 | Foundation | completed | 2026-12-11 | 2026-03-22 | none | observation pending
mil-10055 | prj-5015 | Site preparation | blocked | 2025-10-31 |  | permits | observation pending
mil-10056 | prj-5015 | Finishing | delayed | 2024-08-11 |  | supply_chain | inspector visit done
mil-10057 | prj-5016 | Handover | pending | 2026-05-03 |  | none | inspector visit done
mil-10058 | prj-5016 | Roofing | blocked | 2025-06-15 |  | supply_chain
mil-10059 | prj-5016 | Handover | pending | 2024-07-30 |  | none | inspector visit done
mil-10060 | prj-5016 | Finishing | pending | 2025-12-11 | 2024-08-15 | none | observation pending
mil-10061 | prj-5016 | Handover | completed | 2025-03-17 | 2025-04-12 | none | inspector visit done
mil-10062 | prj-5017 | Finishing | in_progress | 2026-03-14 |  | none | observation pending
mil-10063 | prj-5017 | Foundation | delayed | 2025-01-16 |  | community_consultation
mil-10064 | prj-5017 | Roofing | in_progress | 2024-06-22 |  | none | observation pending
mil-10065 | prj-5018 | Foundation | completed | 2025-01-19 | 2024-12-23 | none
mil-10066 | prj-5018 | Walls | blocked | 2025-08-06 |  | community_consultation | observation pending
mil-10067 | prj-5018 | Foundation | in_progress | 2026-04-13 |  | none | inspector visit done
mil-10068 | prj-5018 | Roofing | delayed | 2026-01-04 |  | funding_gap
mil-10069 | prj-5019 | Site preparation | delayed | 2025-07-24 |  | supply_chain | observation pending
mil-10070 | prj-5019 | Site preparation | completed | 2025-09-07 | 2024-11-01 | none | observation pending
mil-10071 | prj-5019 | Foundation | in_progress | 2025-05-12 |  | none | observation pending
mil-10072 | prj-5020 | Handover | pending | 2024-12-29 |  | none | inspector visit done
mil-10073 | prj-5020 | Walls | completed | 2026-08-10 | 2026-08-30 | none | observation pending
mil-10074 | prj-5020 | Walls | completed | 2026-11-06 | 2026-06-27 | none | observation pending
mil-10075 | prj-5020 | Handover | completed | 2026-07-22 | 2026-02-18 | none
mil-10076 | prj-5020 | Walls | pending | 2024-08-06 | 2024-06-11 | none
mil-10077 | prj-5021 | Walls | in_progress | 2026-12-11 |  | none | inspector visit done
mil-10078 | prj-5021 | Walls | delayed | 2025-06-07 |  | community_consultation | observation pending
mil-10079 | prj-5021 | Roofing | delayed | 2025-03-24 |  | supply_chain | inspector visit done
mil-10080 | prj-5021 | Handover | pending | 2026-12-20 |  | none | observation pending
mil-10081 | prj-5021 | Site preparation | blocked | 2026-05-08 |  | supply_chain | observation pending
mil-10082 | prj-5022 | Finishing | pending | 2025-06-26 |  | none
mil-10083 | prj-5022 | Roofing | completed | 2026-09-16 | 2025-06-07 | none | inspector visit done
mil-10084 | prj-5022 | Walls | delayed | 2025-10-17 |  | permits
mil-10085 | prj-5022 | Handover | pending | 2024-10-17 |  | none
mil-10086 | prj-5023 | Site preparation | completed | 2025-03-27 | 2024-07-13 | none | observation pending
mil-10087 | prj-5023 | Walls | completed | 2026-01-26 | 2025-08-02 | none
mil-10088 | prj-5024 | Handover | in_progress | 2025-11-15 |  | none
mil-10089 | prj-5024 | Walls | in_progress | 2025-04-10 |  | none
mil-10090 | prj-5025 | Handover | delayed | 2025-09-13 |  | supply_chain
mil-10091 | prj-5025 | Roofing | completed | 2025-04-06 | 2024-12-12 | none | observation pending
mil-10092 | prj-5025 | Finishing | in_progress | 2026-05-13 |  | none
mil-10093 | prj-5025 | Finishing | delayed | 2026-08-12 |  | permits
mil-10094 | prj-5026 | Finishing | in_progress | 2024-08-25 |  | none
mil-10095 | prj-5026 | Walls | delayed | 2024-06-24 |  | weather | inspector visit done
mil-10096 | prj-5027 | Handover | completed | 2025-01-29 | 2024-07-15 | none
mil-10097 | prj-5028 | Handover | delayed | 2026-11-09 |  | community_consultation
mil-10098 | prj-5029 | Foundation | pending | 2026-05-23 |  | none
mil-10099 | prj-5029 | Site preparation | pending | 2024-09-02 |  | none | inspector visit done
mil-10100 | prj-5030 | Finishing | in_progress | 2026-03-03 |  | none | observation pending
mil-10101 | prj-5030 | Foundation | delayed | 2025-09-24 |  | weather | observation pending
mil-10102 | prj-5030 | Foundation | completed | 2024-08-21 | 2024-06-23 | none
mil-10103 | prj-5030 | Foundation | delayed | 2026-01-11 |  | weather | inspector visit done
mil-10104 | prj-5031 | Finishing | delayed | 2025-01-20 |  | permits | observation pending
mil-10105 | prj-5031 | Handover | completed | 2025-01-10 | 2024-09-18 | none
mil-10106 | prj-5031 | Site preparation | in_progress | 2024-06-08 |  | none
mil-10107 | prj-5031 | Site preparation | completed | 2026-12-12 | 2026-06-21 | none | observation pending
mil-10108 | prj-5032 | Handover | delayed | 2025-08-31 |  | permits
mil-10109 | prj-5032 | Roofing | completed | 2026-04-26 | 2024-08-07 | none
mil-10110 | prj-5032 | Walls | in_progress | 2026-09-09 |  | none | observation pending
mil-10111 | prj-5032 | Site preparation | completed | 2026-07-03 | 2024-12-12 | none | inspector visit done
mil-10112 | prj-5033 | Roofing | completed | 2026-11-19 | 2025-09-16 | none | observation pending
mil-10113 | prj-5033 | Site preparation | delayed | 2025-09-19 |  | community_consultation | observation pending
mil-10114 | prj-5033 | Walls | delayed | 2026-08-17 |  | supply_chain | observation pending
mil-10115 | prj-5033 | Foundation | pending | 2026-08-20 |  | none | inspector visit done
mil-10116 | prj-5034 | Walls | in_progress | 2024-11-01 |  | community_consultation | inspector visit done
mil-10117 | prj-5035 | Roofing | delayed | 2025-03-12 |  | community_consultation | observation pending
mil-10118 | prj-5035 | Walls | blocked | 2024-11-11 |  | weather
mil-10119 | prj-5035 | Roofing | delayed | 2026-02-13 |  | community_consultation | inspector visit done
mil-10120 | prj-5035 | Handover | completed | 2025-04-12 | 2025-04-20 | none
mil-10121 | prj-5036 | Handover | completed | 2026-02-04 | 2024-10-11 | none
mil-10122 | prj-5036 | Site preparation | in_progress | 2026-05-07 |  | none
mil-10123 | prj-5036 | Handover | completed | 2025-08-02 | 2024-10-05 | none
mil-10124 | prj-5036 | Walls | in_progress | 2026-11-10 |  | none | observation pending
mil-10125 | prj-5037 | Walls | completed | 2025-05-06 | 2025-05-24 | none | inspector visit done
mil-10126 | prj-5037 | Finishing | delayed | 2026-01-08 |  | supply_chain | observation pending
mil-10127 | prj-5037 | Roofing | completed | 2024-06-20 | 2024-06-21 | none
mil-10128 | prj-5038 | Site preparation | completed | 2024-08-23 | 2024-08-07 | none
mil-10129 | prj-5038 | Handover | completed | 2026-08-06 | 2024-12-15 | none
mil-10130 | prj-5038 | Walls | pending | 2026-10-17 |  | none
mil-10131 | prj-5038 | Roofing | in_progress | 2026-02-26 |  | none
mil-10132 | prj-5039 | Finishing | completed | 2025-12-02 | 2024-12-22 | none | inspector visit done
mil-10133 | prj-5039 | Finishing | completed | 2025-03-30 | 2024-07-02 | none | inspector visit done
mil-10134 | prj-5039 | Walls | delayed | 2025-03-17 |  | weather
mil-10135 | prj-5039 | Site preparation | in_progress | 2025-03-31 | 2024-06-13 | none | observation pending
mil-10136 | prj-5039 | Finishing | in_progress | 2026-08-04 |  | none | inspector visit done
mil-10137 | prj-5040 | Walls | in_progress | 2025-03-08 |  | none | observation pending
mil-10138 | prj-5040 | Finishing | in_progress | 2024-10-10 |  | none
mil-10139 | prj-5040 | Finishing | completed | 2024-10-24 | 2024-08-20 | none | observation pending
mil-10140 | prj-5041 | Handover | completed | 2025-04-28 | 2024-12-20 | none
mil-10141 | prj-5042 | Handover | completed | 2026-01-04 | 2024-07-11 | none
mil-10142 | prj-5042 | Finishing | delayed | 2024-10-14 |  | supply_chain
mil-10143 | prj-5043 | Site preparation | delayed | 2024-09-03 |  | community_consultation
mil-10144 | prj-5043 | Handover | completed | 2025-12-11 | 2024-08-03 | none | observation pending
mil-10145 | prj-5044 | Foundation | delayed | 2026-09-12 |  | permits | inspector visit done
mil-10146 | prj-5044 | Roofing | pending | 2026-05-01 | 2025-12-24 | none | inspector visit done
mil-10147 | prj-5045 | Walls | in_progress | 2025-01-25 |  | none
mil-10148 | prj-5046 | Roofing | completed | 2025-07-11 | 2024-06-10 | none
mil-10149 | prj-5046 | Finishing | pending | 2026-06-02 |  | none | inspector visit done
mil-10150 | prj-5046 | Finishing | pending | 2025-01-22 |  | none
mil-10151 | prj-5047 | Finishing | completed | 2026-09-27 | 2024-11-16 | none | inspector visit done
mil-10152 | prj-5047 | Foundation | pending | 2026-03-05 |  | none | observation pending
mil-10153 | prj-5047 | Site preparation | delayed | 2026-07-13 |  | permits | observation pending
mil-10154 | prj-5047 | Foundation | completed | 2025-09-06 | 2024-06-15 | none | observation pending
mil-10155 | prj-5047 | Foundation | in_progress | 2024-07-13 |  | none | inspector visit done
mil-10156 | prj-5048 | Site preparation | delayed | 2025-04-02 |  | permits | observation pending
mil-10157 | prj-5048 | Walls | completed | 2025-01-22 | 2024-10-08 | none
mil-10158 | prj-5048 | Handover | pending | 2026-09-28 |  | none | observation pending
mil-10159 | prj-5048 | Finishing | in_progress | 2025-07-06 |  | none | observation pending
mil-10160 | prj-5049 | Finishing | delayed | 2026-04-15 |  | weather
mil-10161 | prj-5049 | Handover | pending | 2024-06-12 |  | none | observation pending
mil-10162 | prj-5049 | Handover | completed | 2024-11-11 | 2024-06-25 | none | inspector visit done
mil-10163 | prj-5050 | Handover | completed | 2026-11-15 | 2025-06-17 | none | observation pending
mil-10164 | prj-5050 | Roofing | pending | 2026-07-29 |  | none
mil-10165 | prj-5051 | Foundation | delayed | 2026-08-29 |  | weather | observation pending
mil-10166 | prj-5051 | Walls | pending | 2024-08-28 |  | none
mil-10167 | prj-5051 | Site preparation | pending | 2025-12-29 |  | none | inspector visit done
mil-10168 | prj-5051 | Roofing | in_progress | 2025-06-22 | 2024-06-16 | none | observation pending
mil-10169 | prj-5051 | Handover | in_progress | 2024-06-14 |  | none
mil-10170 | prj-5052 | Foundation | completed | 2026-08-31 | 2025-03-01 | permits | inspector visit done
mil-10171 | prj-5052 | Finishing | completed | 2026-09-08 | 2024-06-02 | none
mil-10172 | prj-5053 | Walls | completed | 2026-05-21 | 2025-10-14 | none
mil-10173 | prj-5053 | Walls | in_progress | 2026-02-03 |  | none | inspector visit done
mil-10174 | prj-5053 | Walls | completed | 2025-06-16 | 2025-06-07 | none | inspector visit done
mil-10175 | prj-5053 | Walls | delayed | 2025-05-22 |  | community_consultation
mil-10176 | prj-5054 | Walls | completed | 2026-11-28 | 2025-10-20 | none | observation pending
mil-10177 | prj-5054 | Roofing | blocked | 2024-08-28 |  | permits | observation pending
mil-10178 | prj-5055 | Finishing | delayed | 2024-11-16 |  | supply_chain
mil-10179 | prj-5055 | Foundation | completed | 2026-07-03 | 2024-11-11 | none | inspector visit done
mil-10180 | prj-5055 | Finishing | delayed | 2025-07-11 |  | funding_gap
mil-10181 | prj-5055 | Handover | pending | 2024-06-05 |  | none | inspector visit done
mil-10182 | prj-5056 | Finishing | delayed | 2025-05-09 |  | permits | observation pending
mil-10183 | prj-5056 | Handover | completed | 2025-07-08 | 2024-09-21 | none | observation pending
mil-10184 | prj-5057 | Handover | pending | 2026-03-18 |  | none | inspector visit done
mil-10185 | prj-5057 | Handover | pending | 2026-08-22 |  | none
mil-10186 | prj-5057 | Foundation | blocked | 2025-02-03 |  | funding_gap
mil-10187 | prj-5057 | Site preparation | pending | 2024-07-02 |  | none
mil-10188 | prj-5058 | Walls | blocked | 2025-08-07 |  | none
mil-10189 | prj-5058 | Handover | in_progress | 2024-12-31 |  | none | observation pending
mil-10190 | prj-5059 | Walls | pending | 2025-10-17 | 2025-10-14 | none
mil-10191 | prj-5059 | Handover | delayed | 2026-10-30 |  | weather | observation pending
mil-10192 | prj-5059 | Site preparation | completed | 2026-11-19 | 2025-05-26 | none | observation pending
mil-10193 | prj-5059 | Site preparation | in_progress | 2025-10-13 |  | none
mil-10194 | prj-5060 | Site preparation | delayed | 2026-03-09 |  | supply_chain | observation pending
mil-10195 | prj-5060 | Handover | in_progress | 2025-12-18 |  | none
mil-10196 | prj-5061 | Roofing | delayed | 2026-08-09 |  | funding_gap | inspector visit done
mil-10197 | prj-5061 | Walls | in_progress | 2025-12-31 |  | none
mil-10198 | prj-5062 | Foundation | completed | 2025-10-16 | 2024-11-26 | none
mil-10199 | prj-5062 | Foundation | pending | 2026-02-06 |  | none
mil-10200 | prj-5062 | Roofing | completed | 2025-02-11 | 2024-06-03 | none | inspector visit done
mil-10201 | prj-5063 | Handover | in_progress | 2025-05-15 |  | none | observation pending
mil-10202 | prj-5064 | Roofing | pending | 2024-11-16 |  | none
mil-10203 | prj-5064 | Handover | completed | 2026-08-23 | 2026-05-17 | none
mil-10204 | prj-5064 | Finishing | completed | 2025-08-03 | 2025-01-29 | none | observation pending
mil-10205 | prj-5064 | Roofing | delayed | 2024-08-08 |  | permits | observation pending
mil-10206 | prj-5064 | Site preparation | completed | 2025-02-05 | 2024-08-10 | none | inspector visit done
mil-10207 | prj-5065 | Finishing | completed | 2025-08-31 | 2025-05-04 | none
mil-10208 | prj-5065 | Foundation | in_progress | 2024-08-08 |  | none
mil-10209 | prj-5065 | Site preparation | in_progress | 2025-04-04 |  | none
mil-10210 | prj-5066 | Foundation | pending | 2025-11-20 |  | supply_chain
mil-10211 | prj-5066 | Site preparation | delayed | 2026-08-30 |  | community_consultation | inspector visit done
mil-10212 | prj-5066 | Finishing | in_progress | 2025-12-19 |  | none | inspector visit done
mil-10213 | prj-5067 | Handover | delayed | 2025-10-03 |  | supply_chain | inspector visit done
mil-10214 | prj-5067 | Site preparation | delayed | 2026-10-08 |  | permits | observation pending
mil-10215 | prj-5068 | Roofing | pending | 2025-04-25 | 2024-12-20 | none
mil-10216 | prj-5068 | Roofing | completed | 2026-10-05 | 2025-01-17 | none | inspector visit done
mil-10217 | prj-5068 | Foundation | completed | 2026-08-19 | 2025-11-04 | none | inspector visit done
mil-10218 | prj-5068 | Finishing | completed | 2025-03-22 | 2025-02-10 | none | observation pending
mil-10219 | prj-5069 | Roofing | pending | 2024-08-26 |  | none
mil-10220 | prj-5070 | Walls | completed | 2026-12-27 | 2025-05-16 | none
mil-10221 | prj-5070 | Roofing | delayed | 2025-09-25 |  | funding_gap | inspector visit done
mil-10222 | prj-5071 | Walls | completed | 2025-05-17 | 2025-02-28 | none
mil-10223 | prj-5071 | Walls | completed | 2025-03-05 | 2024-10-26 | none | inspector visit done
mil-10224 | prj-5071 | Walls | blocked | 2025-04-28 |  | permits | inspector visit done
mil-10225 | prj-5072 | Finishing | completed | 2025-02-26 | 2025-01-04 | none | inspector visit done
mil-10226 | prj-5072 | Foundation | delayed | 2024-10-21 |  | funding_gap
mil-10227 | prj-5072 | Foundation | delayed | 2026-01-17 |  | permits | inspector visit done
mil-10228 | prj-5073 | Walls | completed | 2025-05-12 | 2024-09-02 | none | observation pending
mil-10229 | prj-5073 | Foundation | in_progress | 2025-10-09 |  | none
mil-10230 | prj-5073 | Site preparation | in_progress | 2024-08-13 |  | none | observation pending
mil-10231 | prj-5074 | Finishing | delayed | 2025-02-16 |  | funding_gap
mil-10232 | prj-5075 | Roofing | in_progress | 2024-07-23 |  | none
mil-10233 | prj-5075 | Walls | completed | 2025-04-17 | 2024-08-01 | none
mil-10234 | prj-5075 | Foundation | delayed | 2024-07-26 |  | funding_gap
mil-10235 | prj-5076 | Site preparation | blocked | 2026-05-05 |  | funding_gap
mil-10236 | prj-5076 | Finishing | pending | 2026-03-02 |  | none | inspector visit done
mil-10237 | prj-5076 | Foundation | completed | 2026-07-10 | 2025-03-01 | none
mil-10238 | prj-5076 | Foundation | in_progress | 2025-12-19 |  | none | observation pending
mil-10239 | prj-5077 | Roofing | pending | 2024-11-12 |  | none
mil-10240 | prj-5077 | Foundation | pending | 2025-02-08 |  | none | inspector visit done
mil-10241 | prj-5077 | Roofing | blocked | 2025-03-14 | 2024-07-25 | community_consultation | observation pending
mil-10242 | prj-5078 | Finishing | pending | 2024-08-23 |  | none | observation pending
mil-10243 | prj-5078 | Finishing | delayed | 2024-06-24 |  | community_consultation | observation pending
mil-10244 | prj-5079 | Foundation | pending | 2025-11-02 |  | none
mil-10245 | prj-5079 | Walls | delayed | 2026-02-06 |  | supply_chain
mil-10246 | prj-5079 | Finishing | completed | 2025-02-10 | 2024-10-27 | none | observation pending
mil-10247 | prj-5080 | Roofing | blocked | 2026-05-04 |  | community_consultation
mil-10248 | prj-5080 | Roofing | completed | 2025-06-04 | 2024-12-13 | community_consultation | observation pending
mil-10249 | prj-5080 | Roofing | pending | 2025-02-17 |  | none
mil-10250 | prj-5080 | Site preparation | in_progress | 2025-01-11 |  | none | inspector visit done
mil-10251 | prj-5080 | Finishing | blocked | 2025-06-09 |  | supply_chain
mil-10252 | prj-5081 | Foundation | pending | 2024-08-21 |  | none
mil-10253 | prj-5081 | Foundation | delayed | 2025-03-13 |  | funding_gap
mil-10254 | prj-5081 | Finishing | delayed | 2026-02-26 |  | supply_chain
mil-10255 | prj-5081 | Foundation | completed | 2025-08-08 | 2025-09-02 | none
mil-10256 | prj-5082 | Roofing | pending | 2026-08-01 |  | none
mil-10257 | prj-5082 | Foundation | completed | 2025-06-13 | 2025-06-06 | none | inspector visit done
mil-10258 | prj-5082 | Roofing | delayed | 2025-04-30 |  | weather
mil-10259 | prj-5082 | Finishing | pending | 2024-07-20 |  | none
mil-10260 | prj-5083 | Foundation | completed | 2025-09-09 | 2024-08-29 | none | inspector visit done
mil-10261 | prj-5083 | Foundation | completed | 2026-07-13 | 2024-07-14 | none | observation pending
mil-10262 | prj-5083 | Finishing | pending | 2025-09-15 |  | none | observation pending
mil-10263 | prj-5083 | Finishing | completed | 2025-07-19 | 2025-02-24 | none
mil-10264 | prj-5084 | Foundation | delayed | 2025-07-20 |  | supply_chain | observation pending
mil-10265 | prj-5084 | Finishing | delayed | 2024-12-29 |  | permits
mil-10266 | prj-5084 | Foundation | blocked | 2025-06-27 |  | none | observation pending
mil-10267 | prj-5085 | Handover | in_progress | 2026-08-03 |  | none | inspector visit done
mil-10268 | prj-5085 | Roofing | delayed | 2025-07-11 |  | community_consultation
mil-10269 | prj-5085 | Roofing | in_progress | 2026-05-31 |  | none | inspector visit done
mil-10270 | prj-5085 | Walls | blocked | 2025-02-07 |  | weather
mil-10271 | prj-5086 | Finishing | completed | 2025-07-01 | 2025-05-01 | none
mil-10272 | prj-5087 | Walls | delayed | 2025-12-17 | 2025-10-02 | community_consultation
mil-10273 | prj-5087 | Handover | in_progress | 2025-04-14 |  | none | inspector visit done
mil-10274 | prj-5088 | Roofing | in_progress | 2024-06-26 |  | none
mil-10275 | prj-5088 | Walls | completed | 2026-08-27 | 2026-02-18 | none
mil-10276 | prj-5088 | Roofing | in_progress | 2026-08-30 |  | none | observation pending
mil-10277 | prj-5088 | Roofing | delayed | 2024-07-08 |  | weather | inspector visit done
mil-10278 | prj-5089 | Finishing | delayed | 2026-06-20 |  | supply_chain
mil-10279 | prj-5089 | Foundation | in_progress | 2025-07-09 | 2024-09-21 | none | inspector visit done
mil-10280 | prj-5089 | Roofing | completed | 2024-12-16 | 2024-09-15 | none | inspector visit done
mil-10281 | prj-5090 | Walls | in_progress | 2026-12-26 | 2025-01-02 | none
mil-10282 | prj-5090 | Site preparation | delayed | 2026-08-15 |  | supply_chain | observation pending
mil-10283 | prj-5090 | Roofing | pending | 2025-09-14 |  | none
mil-10284 | prj-5091 | Handover | in_progress | 2025-12-24 |  | none
mil-10285 | prj-5091 | Finishing | completed | 2025-11-22 | 2024-11-07 | none
mil-10286 | prj-5091 | Finishing | delayed | 2025-02-07 |  | permits
mil-10287 | prj-5091 | Site preparation | in_progress | 2026-06-12 |  | none
mil-10288 | prj-5091 | Foundation | delayed | 2025-12-21 |  | supply_chain | observation pending
mil-10289 | prj-5092 | Roofing | completed | 2025-10-31 | 2025-06-07 | none | observation pending
mil-10290 | prj-5092 | Handover | completed | 2025-04-03 | 2024-07-12 | none | observation pending
mil-10291 | prj-5092 | Roofing | pending | 2025-04-18 |  | none | inspector visit done
mil-10292 | prj-5092 | Walls | completed | 2024-07-02 | 2024-06-22 | none
mil-10293 | prj-5092 | Roofing | in_progress | 2026-11-18 |  | none | inspector visit done
mil-10294 | prj-5093 | Finishing | in_progress | 2025-02-05 |  | none
mil-10295 | prj-5093 | Foundation | in_progress | 2024-08-24 |  | none
mil-10296 | prj-5093 | Site preparation | completed | 2025-10-18 | 2024-09-03 | none | inspector visit done
mil-10297 | prj-5094 | Handover | in_progress | 2024-10-15 |  | none
mil-10298 | prj-5095 | Site preparation | pending | 2026-12-02 |  | none
mil-10299 | prj-5095 | Roofing | completed | 2026-09-20 | 2024-12-14 | none | observation pending
mil-10300 | prj-5095 | Foundation | pending | 2026-01-29 |  | none
mil-10301 | prj-5096 | Roofing | completed | 2025-02-22 | 2024-08-20 | none
mil-10302 | prj-5097 | Handover | completed | 2024-07-03 | 2024-06-26 | none | inspector visit done
mil-10303 | prj-5097 | Walls | completed | 2025-09-07 | 2024-12-01 | none
mil-10304 | prj-5097 | Walls | completed | 2026-09-13 | 2025-07-16 | none | inspector visit done
mil-10305 | prj-5097 | Site preparation | completed | 2025-01-02 | 2024-08-01 | none | inspector visit done
mil-10306 | prj-5098 | Foundation | completed | 2024-09-29 | 2024-07-08 | none | observation pending
mil-10307 | prj-5099 | Roofing | pending | 2026-07-29 |  | none | observation pending
mil-10308 | prj-5099 | Handover | completed | 2026-03-22 | 2026-04-16 | none
mil-10309 | prj-5100 | Walls | completed | 2024-07-05 | 2024-07-17 | none | inspector visit done
mil-10310 | prj-5100 | Handover | pending | 2024-07-03 |  | none | observation pending
mil-10311 | prj-5101 | Finishing | delayed | 2026-11-01 |  | community_consultation
mil-10312 | prj-5101 | Site preparation | delayed | 2024-12-06 |  | permits | observation pending
mil-10313 | prj-5101 | Foundation | completed | 2025-05-09 | 2024-08-15 | none | inspector visit done
mil-10314 | prj-5101 | Roofing | completed | 2025-10-21 | 2025-03-12 | none | inspector visit done
mil-10315 | prj-5101 | Walls | pending | 2024-06-10 |  | none
mil-10316 | prj-5102 | Walls | completed | 2026-09-23 | 2025-10-27 | none | inspector visit done
mil-10317 | prj-5103 | Roofing | delayed | 2026-07-02 |  | funding_gap | inspector visit done
mil-10318 | prj-5103 | Finishing | delayed | 2026-06-19 |  | funding_gap
mil-10319 | prj-5103 | Roofing | blocked | 2025-09-11 |  | none
mil-10320 | prj-5103 | Finishing | delayed | 2025-08-02 |  | supply_chain
mil-10321 | prj-5104 | Roofing | in_progress | 2026-11-30 |  | none
mil-10322 | prj-5104 | Foundation | in_progress | 2025-11-26 | 2025-01-21 | none | observation pending
mil-10323 | prj-5105 | Site preparation | completed | 2024-08-17 | 2024-09-11 | none | observation pending
mil-10324 | prj-5105 | Roofing | completed | 2026-06-21 | 2026-03-18 | none
mil-10325 | prj-5105 | Roofing | blocked | 2025-01-05 |  | weather | inspector visit done
mil-10326 | prj-5106 | Handover | in_progress | 2025-12-11 | 2024-12-23 | none
mil-10327 | prj-5106 | Foundation | in_progress | 2025-10-05 |  | none
mil-10328 | prj-5106 | Foundation | completed | 2026-04-19 | 2025-02-19 | none | observation pending
mil-10329 | prj-5107 | Site preparation | in_progress | 2026-07-24 |  | none
mil-10330 | prj-5107 | Site preparation | blocked | 2026-11-12 |  | none | inspector visit done
mil-10331 | prj-5107 | Walls | delayed | 2026-08-23 |  | weather | observation pending
mil-10332 | prj-5107 | Site preparation | pending | 2026-07-25 |  | none
mil-10333 | prj-5108 | Handover | pending | 2024-11-28 |  | none
mil-10334 | prj-5108 | Site preparation | pending | 2026-12-23 |  | none
mil-10335 | prj-5108 | Roofing | in_progress | 2025-05-17 |  | none | inspector visit done
mil-10336 | prj-5109 | Finishing | delayed | 2025-05-26 |  | community_consultation
mil-10337 | prj-5109 | Handover | delayed | 2025-07-18 |  | community_consultation
mil-10338 | prj-5109 | Handover | in_progress | 2026-04-04 |  | none
mil-10339 | prj-5109 | Site preparation | in_progress | 2026-12-09 | 2024-07-13 | none
mil-10340 | prj-5109 | Roofing | blocked | 2025-06-17 |  | weather
mil-10341 | prj-5110 | Roofing | delayed | 2026-01-30 |  | supply_chain | observation pending

## Disbursements
disbursement_id | project_id | contract_id | fiscal_year | quarter | amount | payment_status | invoice_ref
dsb-11001 | prj-5001 | ctr-9001 | FY2026 | Q1 | 196750.41 | paid | INV-42248
dsb-11002 | prj-5001 | ctr-9001 | FY2026 | Q2 | 10695.76 | scheduled | INV-49348
dsb-11003 | prj-5002 | ctr-9002 | FY2026 | Q2 | 249820.91 | paid | INV-64005
dsb-11004 | prj-5002 | ctr-9002 | FY2026 | Q4 | 125073.47 | paid | INV-63329
dsb-11005 | prj-5004 | ctr-9006 | FY2026 | Q1 | 35218.76 | paid | INV-88583
dsb-11006 | prj-5004 | ctr-9006 | FY2026 | Q1 | 66785.76 | paid | INV-26217
dsb-11007 | prj-5004 | ctr-9006 | FY2026 | Q2 | 20630.88 | scheduled | INV-50827
dsb-11008 | prj-5004 | ctr-9006 | FY2026 | Q3 | 144763.11 | paid | INV-48955
dsb-11009 | prj-5005 | ctr-9007 | FY2026 | Q1 | 232766.05 | paid | INV-65072
dsb-11010 | prj-5005 | ctr-9007 | FY2026 | Q2 | 13961.31 | scheduled | INV-87110
dsb-11011 | prj-5005 | ctr-9007 | FY2026 | Q1 | 117836.56 | paid | INV-81036
dsb-11012 | prj-5005 | ctr-9007 | FY2026 | Q1 | 140736.43 | pending | INV-20749
dsb-11013 | prj-5006 | ctr-9008 | FY2026 | Q2 | 216806.36 | paid | INV-12207
dsb-11014 | prj-5007 | ctr-9010 | FY2026 | Q1 | 216092.5 | paid | INV-63465
dsb-11015 | prj-5007 | ctr-9010 | FY2026 | Q2 | 144596 | paid | INV-34582
dsb-11016 | prj-5008 | ctr-9011 | FY2026 | Q1 | 167053.69 | scheduled | INV-79177
dsb-11017 | prj-5008 | ctr-9011 | FY2026 | Q1 | 148101.76 | pending | INV-47704
dsb-11018 | prj-5009 | ctr-9012 | FY2026 | Q2 | 151708.72 | scheduled | INV-25022
dsb-11019 | prj-5010 | ctr-9013 | FY2026 | Q2 | 144577.39 | pending | INV-86048
dsb-11020 | prj-5012 | ctr-9017 | FY2026 | Q2 | 63249 | scheduled | INV-19463
dsb-11021 | prj-5012 | ctr-9018 | FY2026 | Q1 | 239890.55 | paid | INV-95439
dsb-11022 | prj-5013 | ctr-9019 | FY2025 | Q3 | 27631.46 | paid | INV-28924
dsb-11023 | prj-5015 | ctr-9021 | FY2026 | Q3 | 103370.58 | paid | INV-99170
dsb-11024 | prj-5015 | ctr-9021 | FY2026 | Q1 | 159127.84 | paid | INV-56291
dsb-11025 | prj-5016 | ctr-9022 | FY2026 | Q2 | 109925.25 | paid | INV-66792
dsb-11026 | prj-5017 | ctr-9023 | FY2026 | Q3 | 187332.75 | paid | INV-36717
dsb-11027 | prj-5017 | ctr-9023 | FY2026 | Q1 | 71578.1 | scheduled | INV-11804
dsb-11028 | prj-5018 | ctr-9024 | FY2026 | Q2 | 161418.25 | paid | INV-46125
dsb-11029 | prj-5018 | ctr-9024 | FY2026 | Q4 | 120607.22 | paid | INV-27496
dsb-11030 | prj-5020 | ctr-9026 | FY2026 | Q1 | 138384.89 | paid | INV-28965
dsb-11031 | prj-5022 | ctr-9028 | FY2026 | Q2 | 164915.16 | pending | INV-62915
dsb-11032 | prj-5022 | ctr-9028 | FY2026 | Q1 | 27672.67 | pending | INV-43043
dsb-11033 | prj-5023 | ctr-9029 | FY2026 | Q2 | 1839.34 | rejected | INV-52909
dsb-11034 | prj-5023 | ctr-9029 | FY2025 | Q2 | 49161.37 | scheduled | INV-50152
dsb-11035 | prj-5023 | ctr-9029 | FY2026 | Q1 | 146961.9 | paid | INV-97796
dsb-11036 | prj-5024 | ctr-9030 | FY2026 | Q1 | 49870.92 | paid | INV-16003
dsb-11037 | prj-5024 | ctr-9030 | FY2026 | Q1 | 133589.01 | paid | INV-66468
dsb-11038 | prj-5024 | ctr-9030 | FY2026 | Q2 | 224085.4 | paid | INV-15751
dsb-11039 | prj-5025 | ctr-9031 | FY2026 | Q2 | 26551.17 | rejected | INV-81901
dsb-11040 | prj-5026 | ctr-9032 | FY2026 | Q1 | 93348.37 | scheduled | INV-11533
dsb-11041 | prj-5028 | ctr-9034 | FY2026 | Q1 | 147567.93 | paid | INV-37405
dsb-11042 | prj-5028 | ctr-9034 | FY2026 | Q1 | 30576 | pending | INV-88423
dsb-11043 | prj-5028 | ctr-9034 | FY2026 | Q1 | 135727.71 | paid | INV-10833
dsb-11044 | prj-5028 | ctr-9034 | FY2026 | Q3 | 103540.44 | paid | INV-21627
dsb-11045 | prj-5029 | ctr-9035 | FY2026 | Q4 | 107349.32 | paid | INV-56779
dsb-11046 | prj-5029 | ctr-9036 | FY2026 | Q2 | 184986.27 | rejected | INV-84934
dsb-11047 | prj-5032 | ctr-9038 | FY2026 | Q3 | 12255.84 | scheduled | INV-37403
dsb-11048 | prj-5033 | ctr-9040 | FY2026 | Q2 | 57180.67 | scheduled | INV-25450
dsb-11049 | prj-5034 | ctr-9041 | FY2026 | Q1 | 190512.06 | pending | INV-66599
dsb-11050 | prj-5034 | ctr-9041 | FY2026 | Q2 | 40608.15 | paid | INV-32462
dsb-11051 | prj-5035 | ctr-9045 | FY2026 | Q1 | 105668.81 | scheduled | INV-30648
dsb-11052 | prj-5036 | ctr-9046 | FY2026 | Q1 | 175222.2 | scheduled | INV-78191
dsb-11053 | prj-5037 | ctr-9048 | FY2026 | Q3 | 249307.2 | paid | INV-84356
dsb-11054 | prj-5037 | ctr-9048 | FY2026 | Q4 | 153126.24 | pending | INV-46592
dsb-11055 | prj-5038 | ctr-9049 | FY2026 | Q4 | 209070.3 | scheduled | INV-48736
dsb-11056 | prj-5039 | ctr-9052 | FY2026 | Q4 | 29721.53 | paid | INV-17050
dsb-11057 | prj-5040 | ctr-9053 | FY2026 | Q2 | 162764.16 | paid | INV-27723
dsb-11058 | prj-5042 | ctr-9055 | FY2026 | Q3 | 13638.78 | pending | INV-81259
dsb-11059 | prj-5043 | ctr-9057 | FY2026 | Q2 | 131743.89 | scheduled | INV-44228
dsb-11060 | prj-5043 | ctr-9058 | FY2026 | Q2 | 11960.62 | paid | INV-36909
dsb-11061 | prj-5043 | ctr-9057 | FY2026 | Q3 | 159426.1 | paid | INV-91899
dsb-11062 | prj-5044 | ctr-9059 | FY2026 | Q2 | 184697.54 | paid | INV-31578
dsb-11063 | prj-5045 | ctr-9060 | FY2026 | Q1 | 195231.84 | pending | INV-13172
dsb-11064 | prj-5045 | ctr-9060 | FY2026 | Q1 | 185807.31 | paid | INV-20625
dsb-11065 | prj-5047 | ctr-9064 | FY2026 | Q1 | 162239.38 | scheduled | INV-92686
dsb-11066 | prj-5048 | ctr-9066 | FY2026 | Q2 | 78898.16 | paid | INV-76062
dsb-11067 | prj-5048 | ctr-9066 | FY2026 | Q3 | 22175.07 | pending | INV-88688
dsb-11068 | prj-5049 | ctr-9067 | FY2026 | Q1 | 192228.79 | scheduled | INV-47876
dsb-11069 | prj-5049 | ctr-9067 | FY2026 | Q1 | 127278.78 | paid | INV-15786
dsb-11070 | prj-5050 | ctr-9068 | FY2026 | Q2 | 95096.04 | paid | INV-21624
dsb-11071 | prj-5050 | ctr-9069 | FY2026 | Q2 | 38339.69 | paid | INV-26114
dsb-11072 | prj-5051 | ctr-9071 | FY2026 | Q3 | 247676.22 | paid | INV-16422
dsb-11073 | prj-5053 | ctr-9072 | FY2026 | Q3 | 11426.42 | paid | INV-91922
dsb-11074 | prj-5054 | ctr-9075 | FY2026 | Q1 | 214150.38 | paid | INV-91014
dsb-11075 | prj-5054 | ctr-9075 | FY2026 | Q3 | 156475.14 | paid | INV-78920
dsb-11076 | prj-5055 | ctr-9076 | FY2026 | Q1 | 232106.51 | pending | INV-43136
dsb-11077 | prj-5056 | ctr-9077 | FY2026 | Q3 | 184888.05 | paid | INV-43903
dsb-11078 | prj-5056 | ctr-9077 | FY2026 | Q2 | 220233.04 | paid | INV-35409
dsb-11079 | prj-5056 | ctr-9078 | FY2026 | Q2 | 162287.9 | paid | INV-41749
dsb-11080 | prj-5057 | ctr-9079 | FY2026 | Q1 | 169797.86 | paid | INV-78383
dsb-11081 | prj-5058 | ctr-9082 | FY2026 | Q1 | 61436.34 | paid | INV-27106
dsb-11082 | prj-5058 | ctr-9082 | FY2026 | Q2 | 108291.37 | scheduled | INV-43010
dsb-11083 | prj-5060 | ctr-9086 | FY2026 | Q1 | 98080.33 | paid | INV-58977
dsb-11084 | prj-5060 | ctr-9086 | FY2026 | Q3 | 101416.52 | paid | INV-98572
dsb-11085 | prj-5060 | ctr-9086 | FY2026 | Q1 | 74164.44 | rejected | INV-13049
dsb-11086 | prj-5062 | ctr-9089 | FY2026 | Q1 | 70667.12 | paid | INV-85459
dsb-11087 | prj-5062 | ctr-9088 | FY2026 | Q3 | 92724.58 | paid | INV-75663
dsb-11088 | prj-5063 | ctr-9090 | FY2026 | Q1 | 116954.99 | pending | INV-18064
dsb-11089 | prj-5063 | ctr-9090 | FY2026 | Q1 | 15323.33 | pending | INV-41302
dsb-11090 | prj-5064 | ctr-9091 | FY2026 | Q1 | 89410.8 | pending | INV-43779
dsb-11091 | prj-5065 | ctr-9092 | FY2026 | Q1 | 36212.6 | scheduled | INV-22396
dsb-11092 | prj-5065 | ctr-9092 | FY2026 | Q2 | 197055.9 | paid | INV-89489
dsb-11093 | prj-5066 | ctr-9093 | FY2026 | Q2 | 50299.55 | paid | INV-63083
dsb-11094 | prj-5066 | ctr-9093 | FY2026 | Q4 | 102255.09 | scheduled | INV-20071
dsb-11095 | prj-5066 | ctr-9093 | FY2026 | Q4 | 126716.72 | pending | INV-52918
dsb-11096 | prj-5066 | ctr-9093 | FY2026 | Q1 | 214736.24 | pending | INV-78743
dsb-11097 | prj-5067 | ctr-9094 | FY2026 | Q4 | 7615.75 | pending | INV-86820
dsb-11098 | prj-5067 | ctr-9094 | FY2026 | Q1 | 137885.37 | pending | INV-78664
dsb-11099 | prj-5067 | ctr-9094 | FY2026 | Q1 | 118595.98 | paid | INV-44588
dsb-11100 | prj-5068 | ctr-9096 | FY2026 | Q4 | 229251.36 | pending | INV-99144
dsb-11101 | prj-5068 | ctr-9096 | FY2026 | Q1 | 87102.35 | pending | INV-19994
dsb-11102 | prj-5070 | ctr-9098 | FY2026 | Q3 | 160182.83 | paid | INV-24267
dsb-11103 | prj-5071 | ctr-9100 | FY2026 | Q1 | 86394.62 | scheduled | INV-28257
dsb-11104 | prj-5071 | ctr-9100 | FY2026 | Q1 | 40261.85 | paid | INV-88900
dsb-11105 | prj-5072 | ctr-9101 | FY2026 | Q1 | 85085.98 | scheduled | INV-43442
dsb-11106 | prj-5072 | ctr-9101 | FY2026 | Q2 | 74193.15 | paid | INV-63378
dsb-11107 | prj-5074 | ctr-9103 | FY2026 | Q3 | 194726.59 | paid | INV-74536
dsb-11108 | prj-5074 | ctr-9103 | FY2026 | Q1 | 186195.53 | paid | INV-22580
dsb-11109 | prj-5074 | ctr-9103 | FY2026 | Q2 | 211787.71 | pending | INV-35288
dsb-11110 | prj-5074 | ctr-9103 | FY2026 | Q2 | 98256.85 | pending | INV-21584
dsb-11111 | prj-5075 | ctr-9104 | FY2026 | Q1 | 19097.17 | pending | INV-37899
dsb-11112 | prj-5075 | ctr-9104 | FY2026 | Q4 | 64252.7 | paid | INV-16822
dsb-11113 | prj-5075 | ctr-9105 | FY2026 | Q2 | 143438.33 | paid | INV-73605
dsb-11114 | prj-5077 | ctr-9106 | FY2026 | Q2 | 208016.49 | paid | INV-15287
dsb-11115 | prj-5079 | ctr-9110 | FY2026 | Q1 | 112410.07 | scheduled | INV-49117
dsb-11116 | prj-5080 | ctr-9111 | FY2026 | Q1 | 161638.76 | paid | INV-26270
dsb-11117 | prj-5082 | ctr-9116 | FY2026 | Q2 | 205741.96 | paid | INV-83985
dsb-11118 | prj-5082 | ctr-9115 | FY2026 | Q3 | 46262.73 | scheduled | INV-69389
dsb-11119 | prj-5083 | ctr-9117 | FY2026 | Q1 | 143624.06 | pending | INV-65146
dsb-11120 | prj-5083 | ctr-9117 | FY2026 | Q3 | 207740.26 | paid | INV-88683
dsb-11121 | prj-5083 | ctr-9117 | FY2026 | Q1 | 37150.08 | pending | INV-85927
dsb-11122 | prj-5083 | ctr-9117 | FY2026 | Q2 | 37586.03 | paid | INV-48588
dsb-11123 | prj-5085 | ctr-9120 | FY2026 | Q2 | 214351.82 | rejected | INV-34952
dsb-11124 | prj-5085 | ctr-9119 | FY2026 | Q1 | 205022.05 | paid | INV-28519
dsb-11125 | prj-5086 | ctr-9123 | FY2026 | Q1 | 234444.73 | paid | INV-13009
dsb-11126 | prj-5086 | ctr-9124 | FY2026 | Q2 | 30311.45 | pending | INV-14000
dsb-11127 | prj-5086 | ctr-9124 | FY2026 | Q1 | 78065.94 | pending | INV-39898
dsb-11128 | prj-5087 | ctr-9125 | FY2026 | Q1 | 227057.14 | paid | INV-78184
dsb-11129 | prj-5087 | ctr-9125 | FY2026 | Q2 | 5357.32 | pending | INV-47316
dsb-11130 | prj-5088 | ctr-9126 | FY2026 | Q4 | 30333.51 | scheduled | INV-84221
dsb-11131 | prj-5088 | ctr-9126 | FY2026 | Q1 | 212393.96 | scheduled | INV-87399
dsb-11132 | prj-5088 | ctr-9126 | FY2026 | Q2 | 165568.73 | scheduled | INV-82170
dsb-11133 | prj-5089 | ctr-9127 | FY2026 | Q1 | 230941.89 | paid | INV-83635
dsb-11134 | prj-5090 | ctr-9128 | FY2026 | Q1 | 220689.43 | pending | INV-79272
dsb-11135 | prj-5090 | ctr-9128 | FY2026 | Q2 | 187855.02 | paid | INV-35171
dsb-11136 | prj-5091 | ctr-9129 | FY2026 | Q2 | 199274.61 | paid | INV-76719
dsb-11137 | prj-5091 | ctr-9129 | FY2026 | Q2 | 8334.07 | rejected | INV-72707
dsb-11138 | prj-5091 | ctr-9129 | FY2026 | Q1 | 128960.75 | paid | INV-61024
dsb-11139 | prj-5094 | ctr-9133 | FY2026 | Q2 | 167410.45 | pending | INV-53888
dsb-11140 | prj-5094 | ctr-9132 | FY2026 | Q1 | 132425.28 | paid | INV-46601
dsb-11141 | prj-5094 | ctr-9132 | FY2026 | Q1 | 214601.37 | paid | INV-69393
dsb-11142 | prj-5095 | ctr-9134 | FY2026 | Q3 | 218088.32 | pending | INV-94157
dsb-11143 | prj-5096 | ctr-9135 | FY2026 | Q1 | 159738.22 | paid | INV-74915
dsb-11144 | prj-5097 | ctr-9136 | FY2026 | Q1 | 235789.8 | pending | INV-62850
dsb-11145 | prj-5098 | ctr-9137 | FY2026 | Q2 | 86793.07 | paid | INV-22067
dsb-11146 | prj-5098 | ctr-9137 | FY2026 | Q2 | 230784.4 | pending | INV-31098
dsb-11147 | prj-5098 | ctr-9137 | FY2026 | Q3 | 99922.45 | paid | INV-79931
dsb-11148 | prj-5099 | ctr-9138 | FY2026 | Q1 | 23207.52 | scheduled | INV-51182
dsb-11149 | prj-5100 | ctr-9141 | FY2026 | Q1 | 100926.76 | paid | INV-20374
dsb-11150 | prj-5102 | ctr-9144 | FY2026 | Q3 | 41903.95 | scheduled | INV-89026
dsb-11151 | prj-5102 | ctr-9144 | FY2026 | Q1 | 187834.08 | paid | INV-77278
dsb-11152 | prj-5103 | ctr-9145 | FY2026 | Q1 | 143785.48 | paid | INV-25894
dsb-11153 | prj-5103 | ctr-9145 | FY2026 | Q1 | 167301.16 | paid | INV-44681
dsb-11154 | prj-5103 | ctr-9145 | FY2026 | Q2 | 145122.82 | scheduled | INV-61850
dsb-11155 | prj-5103 | ctr-9145 | FY2026 | Q2 | 24534.54 | paid | INV-16933
dsb-11156 | prj-5104 | ctr-9146 | FY2026 | Q2 | 100191.53 | paid | INV-28582
dsb-11157 | prj-5105 | ctr-9149 | FY2026 | Q3 | 43409.23 | scheduled | INV-11836
dsb-11158 | prj-5105 | ctr-9147 | FY2026 | Q2 | 223672.29 | paid | INV-33906
dsb-11159 | prj-5105 | ctr-9147 | FY2026 | Q2 | 232715.8 | paid | INV-85041
dsb-11160 | prj-5105 | ctr-9149 | FY2026 | Q1 | 196314.24 | paid | INV-67400
dsb-11161 | prj-5106 | ctr-9150 | FY2026 | Q3 | 205813.49 | paid | INV-25071
dsb-11162 | prj-5107 | ctr-9151 | FY2026 | Q2 | 102697.87 | paid | INV-85028
dsb-11163 | prj-5107 | ctr-9151 | FY2026 | Q4 | 196616.31 | paid | INV-93447
dsb-11164 | prj-5107 | ctr-9151 | FY2026 | Q1 | 30629.75 | paid | INV-18007
dsb-11165 | prj-5108 | ctr-9152 | FY2026 | Q1 | 195191.58 | scheduled | INV-12026
dsb-11166 | prj-5109 | ctr-9153 | FY2026 | Q1 | 165068.72 | scheduled | INV-39348
dsb-11167 | prj-5110 | ctr-9154 | FY2026 | Q2 | 98945.84 | pending | INV-57977
dsb-11168 | prj-5110 | ctr-9154 | FY2026 | Q3 | 112373.3 | scheduled | INV-44722